# **UXG Content Development Process**

|  |  |  |  |
| --- | --- | --- | --- |
| **Status Label** | **Description** | **Required, optional tasks** | **Exit criteria** |
| New Entry | New topic identified | Topic identified by user studies or HFE | * Collaborative review by HFE and BAC |
| Backlog | Topic added to backlog | * New topic entered into backlog * Topic aligned to Epic (optional) * Backlog reviewed at least monthly * Get user feedback on priorities (optional) * Get feedback from Content Development Team (CDT) on priorities (optional) | * Topic prioritized by HFE * Analyst assigned from BAC * Content Technical Lead identified |
| Analyzing | UXG team is working on requirements specification | * Purpose of the content specified * User Stories written, including user role(s), corresponding goals and context of use * Information sources identified * Author, SMEs, stakeholders identified * Related UXG content identified * Content type specified (optional wireframes created) * Content evaluation planned (incl no user testing needed) * Get user feedback (optional) * Get feedback from CDT (optional) | * All requirements are met |
| Reviewing | Content proposal is under review | * HFE reviews plan for content development work * Content delivery schedule approved by HFE & BAC * Define timeline | * Effort scheduled * Author, SMEs committed * HFE approved |
| Authoring | Content is being authored | * Communicate QA requirements with author * Content drafted in templates * Finalize wireframes of new content types through user studies (optional) * Reviewed by users (optional) | * Reviewed by BAC Content QA * Reviewed by SMEs |
| Authoring Complete | Authored content is approved by BAC and SMEs | * Content ready for HFE review * Content not assigned for development until HFE has approved content | * Content assigned for development in WordPress |
| Building | Content is being developed | * Content developed in WordPress * Produce user evaluation study plan and obtain HFE approval. * Define outcome measures for testing (and monitoring once published?) | * Approved by SME * Approved by BAC Development QA * Approved user evaluation plan |
| Building Complete | WordPress code is evaluated by users | User evaluation (formative testing) executed on WordPress build.  Changes to build approved.  Build changes implemented. | * User evaluation plan executed * WordPress code approved by HFE * Code is published |
| Published | Content is published on the UX Guide | Content usage monitored | * Are learning objectives achieved? * Are intended use objectives achieved? |
| On Hold | Work has paused | Solicit management to get involved | TBD |
| Abandoned | Decision made to discontinue work | After-action review (optional) | N/A |