## Sheet1
Objectives (Airtable 26feb PM) | Deliverables (Airtable 26feb PM removed items; Tom's new items) | Tom's Notes
Align UXG work to business goals and measurable objectives | UXG Stakeholder needs assessment | This Objective includes ongoing maintenance of Airtable > ProjectManagement. Not sure how to define "Stakeholder" or assess their needs.
| Plan Release 2 objectives and scope | Should this be generic, like "Plan future release objectives and scope"?
| Process for managing UXG user and stakeholder needs | This requires clarification.
| Work management | This requires clarification … is it define and assign Activities for two week time periods?
Get approval of Business Goals and their measurement from HFE leadership
Periodically review, update and get approval on Business Goals
Assign Objectives for each Business Goal
Develop the UXG information architecture that supports a scalable CMS | Jan proto's Home page | Scalable CMS is likely a separate Objective from "information architecture" … not sure what to do regarding CMS objective. For each page type within the overall IA, we will need to follow a process like this -- 1. define then research content sources 2. identify instances of content type (e.g., Heuristic Evaluation and Usability Testing are instances of Method) 3. determine structure and/or primary & other properties of content 4 (design). create wireframes for layout/grouping/prominence of content 5 (design). create visual/aesthetic design based on wireframes 6 (design). build visual design within Wordpress 4 (content). write content drafts 5 (content). edit/QA content iteratively 6 (content). stage final content for Wordpress build 7. perform Wordpress build 8. QA Wordpress iteratively 8. build Wordpress iteratively until it passes QA
Key Concepts and other content under Jan proto's Fundamental Concepts
Jan proto's UX Process including Business Process, Situational Playbooks, etc.
HCD phase content based on ISO standard
Jan proto's Methods, including Workflow Management
Create the method template (Divi)
Heuristic Eval content creation
| Playbooks including Value Management | This requires clarification … would it be under Methods like Situational Playbooks is? Or under Resources perhaps?
| Review IPS guidance on Error Dialogs | This needs clarification … would this fit under Methods > Design?
Glossary of terms including terms for each Method (e.g., Heuristic Evaluation)
Jan proto's Resources including Videos, Personas, Tools (inc. Workflow Management), Case Studies
Videos including Key Concepts
Jan proto's Help
Jan proto's Search
Jan proto's Contact Us
Jan proto's Provide Feedback
Prepare the UXG for VISN 4 usability training | Determine curriculum from trainer
Define page types and content instances to support curriculum
| Create and build pages | See notes in row 10.
Determine if other assets are needed to support curriculum other than UXG, then create those assets
Prepare UXG site for stakeholder demo | Define page types and content instances to support demo
Specify and create Demo Theme in Wordpress
| Create and build pages | See notes in row 10.
Prepare UXG site to get feedback from end users | Define usability test plan
Define page types and content instances to support usability testing
Create prototype in Adobe XD or other prototyping tool (not Wordpress)
Define test subject attributes and sources, then recruit users
Run tests
Write test report
Define changes to UXG design based on results
| Create and build pages in Adobe XD | See notes in row 10.
Update the UXG glossary with terms from other VA orgs | [same Deliverable, different Objective] Glossary of terms including terms for each Method (e.g., Heuristic Evaluation)
Produce HCD guidance for HIS projects (based on ISO standards) | [same Deliverable, different Objective] Jan proto's UX Process including Business Process, Situational Playbooks, etc.
Produce content explaining technical UX concepts (with video snippets) |  | Is this a Deliverable under UXG Information Architecture (Fundamental Concepts)?
Establish competency for managing user needs and context of use |  | Is this a Deliverable under "Align UXG work to business goals and measurable objectives"?
Incorporate content from other organizations and other content development efforts |  | Is this a Deliverable under UXG Information Architecture?
Other | Replace veteransaffairsuxguide.com/ | Is this an Objective and not a Deliverable? We can break it down into the specific pages from the live site that will need to be replaced.
| Present on HFE BrownBag | Is this a Deliverable under Stakeholder Demo, or is it its own Objective which requires breaking it down into the specific pages required?
Value Management Playbook
Key concepts explained (for video snipets) - HEURISTIC EVALUATION for Release 1
Video snipets describing key concepts
UX Guide Information Architecture