## Project Status
[6 empty] | Status Key: | Planning
On track
At Risk
Delayed
Not Started
Complete
Project Title | HFE POC | Proposal Complete Date | Proposal Acceptance Date | Study Plan Complete Date | Report Complete Date | Debrief/AAR Complete Date | Status | Notes
UXG Stakeholder Needs Assessment | Ross Speir | 2019-10-29 | 2019-10-31 | TBD |  |  | On track | Kickoff with BAC team expected week of Nov 4th

## DERAIL
DERAIL (Decisions, Expectations (with assumptions), Risks, Actions, Issues Log)
Type (DERAIL) | Title | Status: Open, Closed | Who Identified | Action Owner | Date Opened | Target Close Date | Date Closed | Assumptions | Dependencies | Notes [add incremental notes, date/stamp, and Risk Prob (low, medium, high) and Impact (low, medium, high)] | Next Step(s): | Resolution Summary Notes (Accept, Mitigate, Transfer, Avoid)
Decision | Define stakeholders for interviews and schedule interviews | Open | Ross | Ross | 2019-11-01 | TBD | TBD | Conduct all the interviews the week of Nov. 11th. | Availability to stakeholders for interviews | 11/1/2019: Ross will identify stakeholders (3-4 of them) to participate in a 30-60 minute remote interview with BAC HFE team. | Stakeholder interviews should occur after BAC team discovery meetings with Ross and initial familiarization with UXG website.
Decision | 5 Stakeholders have been identified | Open | Ross | Ross | 2019-11-11 | TBD | TBD | Conduct all the interviews the week of Nov. 11th. | Availability to stakeholders for interviews | 11/1/2019: Ross has identified 5 Stakeholders. BAC HFE team would like to schedule an additional interview with one CAC. | Schedule interviews for week of 11/11/2019
Risk | Deliverable pushed out to Nov 27th | Open | Ross | Ross | 2019-11-15 | TBD | TBD | Conduct all the interviews the week of Nov. 18th | Availability to stakeholders for interviews - Still waiting to schedule 3 stakeholders the week of Nov 18th | 11/15/2019: Due to scheduling, we were not able to interview all stakeholders the week of Nov 11th. We will continue interviewing stakeholders the week of Nov 18th. We need 2 days after the last Stakeholder to prepare the report - that would make the deliverable date Nov 27th. | Schedule interviews for week of 11/18/2019

## Project Team Members
Organization | Name | Funtion/Title | Core Project Team Y/N | Decision Maker, Influencer, Interested | Phone | Email | Project counterpart | Notes
Govt HFE | Ross Speir | UXG Program Manager | Y |  |  | Ross.Speir2@va.gov
BAC | Alaina Wood | HFE Lead | Y |  | (424) 298-7441 | alainawood@usabilityfarm.com
BAC | Braxton Hicks | HFE Support | Y |  | (704) 807-4678 | whhicks@ncsu.edu
BAC | Eric Wald | Senior Designer/Wordpress Developer | Y |  | (919) 455-1449 | erobertwald@gmail.com
BAC | Jessica Howe | HFE Lead | Y |  | (202) 877-2452 | jessica.l.howe@medstar.net
BAC | David Clarke | BAC Project Manager | Y |  | (919) 656-4955 | davidclarke@bacteam.com
Stakeholders for Interviews:

## Dropdown options (hidden)
Derail Options
Decision
Expectation
Risk
Action
Issue Log
Status
Open
Closed