## Sheet1
Airtable's June Objectives | Activities and associated pages or content types
Integrate CPRS design document into UXG | design+content: Home, Fundamental Concepts > (possibly) Displays & Controls, Process > Produce, Methods > "UI Design Audit" (already drafted), (possibly) Methods > "Final Concept (Visualization)" and "Prototyping", Resources > Quick Start Guide, (possibly) Resources > Playbook, (possibly) Resources > Tools > Style Guidelines
user study: CPRS Quick Start Guide for early adopter CACs, (possibly) Playbook for CHIO team project;
CPRS design pattern: Kas document :: digest and breakdown into what portions in HTML and what portion as external document.
Management of UXG Content Development team
Discovery: How we might the UX Guide support the VHA's HCD Workgroup | content: content inventory of OPM "Lab" … plus more sources listed in Airtable
Deliver UX materials for CACs building CRDTs (Quick Start Guide - QSG) | same items as in B2, above
Recruit and manage a group of UX ‘early adopter’ CACs for UXG work (Process improvement) | user study: May Playbook for interested CACs
Deliver workflow modeling content (from Visionary) | user study: Playbook for CHIO team project; design+content: Fundamental Concepts > (possibly) Sequence & Flow, Process > Understand and Produce, Methods > "Clinical Workflow Modeling" (already drafted), (possibly) Resources > Playbook
Digest and breakdown into what portions in HTML and what portion as external document.
Maps to a current Method - content
Implement value management practices (Process improvement)
How might the UXG support the VA AMIA 10x10 Informatics Certification Training (Discovery) | Of the eight topics in AMIA schedule, UXG could provide content covering these topics -- == "Clinical Workflow Analysis, Process Redesign & Quality Improvement": Fundamental Concepts > (possibly) Sequence & Flow, Process > Understand and Produce, Methods > "Clinical Workflow Modeling" (already drafted), (possibly) Resources > Playbook == "Human Factors Engineering": need more info on this topic to determine what sections of UXG could provide support
Demo UXG site to HFE stakeholders | not clear whether this is now end of June or some time in July
Create a case study of the Self-Alerts project (VACI project) | need more details on this design+content: Resources > Case Study, (possibly) Resources > Videos
Conduct user research: CHIO team
Below are items not listed in June Objectives
Gaps in site org | design+content: Fundamental Concepts landing page, Process > All Phases, Training landing page, landing pages for Resources > Tools, Personas, Case Studies, Videos, Newsletters, FAQs, Resources > Tools > Style Guidelines
Gaps in May interactive wireframes | Any link in the wires should be active … find existing content that we can link to or possibly create new content on a limited and strategic basis
Document a strategy for deciding what to do next | discovery: How to move items from Discovery > Airtable to UXG backlog content: How to leverage Tuesday Content Team; analyze all User Stories in Airtable > Discovery